## Budget
| 6th graders | Team 5969 | 4th graders | Team 6757
Tournament | 50 |  | 871.79
Field Kit | 65
Registration | 200
xtra Battery | 54.95
Shipping | 19.2
Tax | 26.4
Total | 415.55 |  | 871.79
Per Person | 83.11 |  | 217.9475

## Sheet1 (hidden)
Mission | Pt | Time | Order | Owner | Due date | Status | Details
14 | 10 | 8 |  | Katie | 2008-11-22 | started | Was Natalie, now Alyssa or Katie
1 | 25 | 8 |  | Natalie | 2008-11-22 | started

## Summary (hidden)
|  |  | 3240 |  | 7
[6 empty] | Values | Status
[6 empty] | Sum of Pt |  |  | Sum of Time |  |  | Total Sum of Pt | Total Sum of Time
| Owner | Mission | Due date | Order | Details | started | Not started | (blank) | started | Not started | (blank)
| Alyssa | 5 | 11/15/08 |  |  |  | 40 |  |  | 8 |  | 40 | 8
|  | 12 | 2008-12-01 | (blank) | (blank) |  | 10 |  |  | 8 |  | 10 | 8
|  |  |  | (blank) Total |  |  | 10 |  |  | 8 |  | 10 | 8
| Alyssa Total | [5 empty] | 50 |  |  | 16 |  | 50 | 16
| Natalie | 1 | 2008-11-22 | (blank) | (blank) | 25 |  |  | 8 |  |  | 25 | 8
|  |  |  | (blank) Total |  | 25 |  |  | 8 |  |  | 25 | 8
| Natalie Total |  |  |  |  | 25 |  |  | 8 |  |  | 25 | 8
| Katie | 14 | 2008-11-22 | (blank) | Was Natalie, now Alyssa or Katie | 10 |  |  | 8 |  |  | 10 | 8
|  |  |  | (blank) Total |  | 10 |  |  | 8 |  |  | 10 | 8
| Katie Total |  |  |  |  | 10 |  |  | 8 |  |  | 10 | 8
| (blank) | (blank) | (blank) | (blank) | (blank) |  |  | 0 |  |  |  | 0
|  |  |  | (blank) Total |  |  |  | 0 |  |  |  | 0
| (blank) Total | [6 empty] | 0 |  |  |  | 0
| Grand Total |  |  |  |  | 35 | 50 | 0 | 16 | 16 |  | 85 | 32
Order | Program | Attachment | Position | Name | Tasks | Mission | Pt | Time | Order | Owner | Due date | Status | Details
[5 empty] | TARGET SPOT Required Condition: Parked with at least one of its drive wheels or treads touching the round target |  | = 25 Points
leveeGETbuoy
96 |  |  |  | Computer | Move computer to green grid area (near house) for 10 pts | 14 | 10 | 8 |  | Katie | 2008-11-22 | started | Was Natalie, now Alyssa or Katie
97 |  |  |  | Align Arrows | Align 2 shared Yellow Arrows in same direction | 5 | 40 | 8 | Next to last | Alyssa | 2008-11-15 | Not started | Wait until last to program
98 |  |  |  | Drilling Machine | 10 pts for raising the drill assembly | 12 | 10 | 8 |  | Alyssa | 2008-12-01 | Not started
99 |  |  |  | Raise House | Raise House | 1 | 25 | 8 |  | Natalie | 2008-11-22 | started
|  |  |  | 85 | 32
150
8.3333

## 2010 Schedule
week | Date | GENERAL | ROBOT GAME | NOTES | PROJECT | NOTES
1 | 2011-08-19 | Check Game Q&A & FLL website | Build Field Set up Kit | Done | Share challenge info Related problems Brainstorm research | Done
2 | 2011-08-27 | Goals: 1/2 missions? point level, have fun | Read Missions & Q&A Design chassis Simple programs Learn sensors Discuss strategy | Today: | Share research Select problem Begin solutions Pick someone to interview |  | logic using switch statement
3 | 2011-09-03 | Check Game Q&A & FLL website | Finish design Perform easiest 2 missions Strategy & design for other missions |  | Share research Brainstorm Solutions |  | using touch sensor, calibrating light sensor.
4 | 2011-09-10 | Check Game Q&A & FLL website | Design and program robot 50% of robot related goals |  | Decide on the problem How will team share findings?
5 | 2011-09-17 | Check Game Q&A & FLL website Re-assess Team Goals | Make sure all scoring strategies are legal & worth points Update missions & rules if they change Sequence Missions |  | Finish preparing materials to share findings Brainstorm what to present
6 | 2011-09-24 | Check Game Q&A & FLL website | 25% of robot related goals and increase reliability |  | Finish preparing materials to share findings Brainstorm what to present
7 | 2011-10-01 | Check Game Q&A & FLL website Finalize Team Goals | 50 % of robot goals, most of the time. Test in different lighting conditions. |  | Begin writing up presentation
8 | 2011-10-08 | Check Game Q&A & FLL website | 75 % of robot goals, most of the time. Test in different lighting conditions. |  | Finish writing up presentation
9 | 2011-10-15 |  | 100 % of robot goals, most of the time. Test in different lighting conditions. |  | Final touches on presentation. Rehearse to 5 minute time limit.
10 | 2011-10-22 |  | Complete Fine Tuning Make sure all robot related goals can be met |  | Fine tune presentation. Practice Q&A
11 | 2011-10-29 |  |  |  | Dry Run
12 | 2011-11-05 | 1st Level Tourament
13 | 2011-11-12 | 2nd level Tournament
14 | 2011-11-19 | 2nd level Tournament
|  | Documents |  |  | Owner | Backup
|  | Field Set Up | Make sure everything is right |  | Kristina | Jessica
|  | Rules | Make sure we follow rules |  | Alyssa | Athena
|  | Game Q&A | Keep the team up to date |  | Alyssa | Athena
Jobs:
|  | Research | Jessica |  | Gather info for the challenge
|  | Presentation | Grace |  | Create presentation
|  | Chassis/Design | Natalie |  | decisions about the design of the robot
|  | Programming | Katie |  | decisions about programming the robot
|  | Resource Manager | Alyssa
|  | Project Management | Erikka |  | keep project on track, agree to schedules
|  | Tournament Manager | Arshia
|  | Mission Manager | Kristina
| Mins | Meetings
| 5 | Review Progress
| 5 | Q&A Updates
| 45 | Programming/Building
| 5 | Break
| 45 | Programming/Building
| 10 | Wrap up
| 5 | Clean up
120
Formulas:
Date = [Date, row above]+7

## Missions
Order | Mission | Name | Goals | Points | Owner | Time | Order | Difficulty | Mission Name | Notes | Predecessors | Due Date | Status | PossiblePts