## Budget
| 6th graders | Team 5969 | 4th graders | Team 6757
Tournament | 50 |  | 871.79
Field Kit | 65
Registration | 200
xtra Battery | 54.95
Shipping | 19.2
Tax | 26.4
Total | 415.55 |  | 871.79
Per Person | 83.11 |  | 217.9475

## Sheet1 (hidden)
Mission | Pt | Time | Order | Owner | Due date | Status | Details
14 | 10 | 8 |  | Katie | 2008-11-22 | started | Was Natalie, now Alyssa or Katie
1 | 25 | 8 |  | Natalie | 2008-11-22 | started

## Summary (hidden)
|  |  | 3240 |  | 7
[6 empty] | Values | Status
[6 empty] | Sum of Pt |  |  | Sum of Time |  |  | Total Sum of Pt | Total Sum of Time
| Owner | Mission | Due date | Order | Details | started | Not started | (blank) | started | Not started | (blank)
| Alyssa | 5 | 11/15/08 |  |  |  | 40 |  |  | 8 |  | 40 | 8
|  | 12 | 2008-12-01 | (blank) | (blank) |  | 10 |  |  | 8 |  | 10 | 8
|  |  |  | (blank) Total |  |  | 10 |  |  | 8 |  | 10 | 8
| Alyssa Total | [5 empty] | 50 |  |  | 16 |  | 50 | 16
| Natalie | 1 | 2008-11-22 | (blank) | (blank) | 25 |  |  | 8 |  |  | 25 | 8
|  |  |  | (blank) Total |  | 25 |  |  | 8 |  |  | 25 | 8
| Natalie Total |  |  |  |  | 25 |  |  | 8 |  |  | 25 | 8
| Katie | 14 | 2008-11-22 | (blank) | Was Natalie, now Alyssa or Katie | 10 |  |  | 8 |  |  | 10 | 8
|  |  |  | (blank) Total |  | 10 |  |  | 8 |  |  | 10 | 8
| Katie Total |  |  |  |  | 10 |  |  | 8 |  |  | 10 | 8
| (blank) | (blank) | (blank) | (blank) | (blank) |  |  | 0 |  |  |  | 0
|  |  |  | (blank) Total |  |  |  | 0 |  |  |  | 0
| (blank) Total | [6 empty] | 0 |  |  |  | 0
| Grand Total |  |  |  |  | 35 | 50 | 0 | 16 | 16 |  | 85 | 32
Order | Program | Attachment | Position | Name | Tasks | Mission | Pt | Time | Order | Owner | Due date | Status | Details
[5 empty] | TARGET SPOT Required Condition: Parked with at least one of its drive wheels or treads touching the round target |  | = 25 Points
leveeGETbuoy
96 |  |  |  | Computer | Move computer to green grid area (near house) for 10 pts | 14 | 10 | 8 |  | Katie | 2008-11-22 | started | Was Natalie, now Alyssa or Katie
97 |  |  |  | Align Arrows | Align 2 shared Yellow Arrows in same direction | 5 | 40 | 8 | Next to last | Alyssa | 2008-11-15 | Not started | Wait until last to program
98 |  |  |  | Drilling Machine | 10 pts for raising the drill assembly | 12 | 10 | 8 |  | Alyssa | 2008-12-01 | Not started
99 |  |  |  | Raise House | Raise House | 1 | 25 | 8 |  | Natalie | 2008-11-22 | started
|  |  |  | 85 | 32
150
8.3333

## 2010 Schedule
week | Date | GENERAL | ROBOT GAME | NOTES | PROJECT | NOTES
1 | 2011-08-19 | Check Game Q&A & FLL website | Build Field Set up Kit | Done | Share challenge info Related problems Brainstorm research | Done
2 | 2011-08-27 | Goals: 1/2 missions? point level, have fun | Read Missions & Q&A Design chassis Simple programs Learn sensors Discuss strategy | Today: | Share research Select problem Begin solutions Pick someone to interview |  | logic using switch statement
3 | 2011-09-03 | Check Game Q&A & FLL website | Finish design Perform easiest 2 missions Strategy & design for other missions |  | Share research Brainstorm Solutions |  | using touch sensor, calibrating light sensor.
4 | 2011-09-10 | Check Game Q&A & FLL website | Design and program robot 50% of robot related goals |  | Decide on the problem How will team share findings?
5 | 2011-09-17 | Check Game Q&A & FLL website Re-assess Team Goals | Make sure all scoring strategies are legal & worth points Update missions & rules if they change Sequence Missions |  | Finish preparing materials to share findings Brainstorm what to present
6 | 2011-09-24 | Check Game Q&A & FLL website | 25% of robot related goals and increase reliability |  | Finish preparing materials to share findings Brainstorm what to present
7 | 2011-10-01 | Check Game Q&A & FLL website Finalize Team Goals | 50 % of robot goals, most of the time. Test in different lighting conditions. |  | Begin writing up presentation
8 | 2011-10-08 | Check Game Q&A & FLL website | 75 % of robot goals, most of the time. Test in different lighting conditions. |  | Finish writing up presentation
9 | 2011-10-15 |  | 100 % of robot goals, most of the time. Test in different lighting conditions. |  | Final touches on presentation. Rehearse to 5 minute time limit.
10 | 2011-10-22 |  | Complete Fine Tuning Make sure all robot related goals can be met |  | Fine tune presentation. Practice Q&A
11 | 2011-10-29 |  |  |  | Dry Run
12 | 2011-11-05 | 1st Level Tourament
13 | 2011-11-12 | 2nd level Tournament
14 | 2011-11-19 | 2nd level Tournament
|  | Documents |  |  | Owner | Backup
|  | Field Set Up | Make sure everything is right |  | Kristina | Jessica
|  | Rules | Make sure we follow rules |  | Alyssa | Athena
|  | Game Q&A | Keep the team up to date |  | Alyssa | Athena
Jobs:
|  | Research | Jessica |  | Gather info for the challenge
|  | Presentation | Grace |  | Create presentation
|  | Chassis/Design | Natalie |  | decisions about the design of the robot
|  | Programming | Katie |  | decisions about programming the robot
|  | Resource Manager | Alyssa
|  | Project Management | Erikka |  | keep project on track, agree to schedules
|  | Tournament Manager | Arshia
|  | Mission Manager | Kristina
| Mins | Meetings
| 5 | Review Progress
| 5 | Q&A Updates
| 45 | Programming/Building
| 5 | Break
| 45 | Programming/Building
| 10 | Wrap up
| 5 | Clean up
120
Formulas:
Date = [Date, row above]+7

## Missions
Order | Mission | Name | Goals | Points | Owner | Time | Order | Difficulty | Mission Name | Notes | Predecessors | Due Date | Status | PossiblePts
1 | 5 | Mechanical Arm Patent | Patent is grabbed by your sides hand | 25 | Natalie | 10 | 1 |  | CLAW |  | w/ Mission 3.0&4.0 |  | 100% | 25
1 | 6 | Bionic Eyes | At Least One Eye Touching Upper Body | 20 | Katie | 10 | 13 | [5 empty] | Open | 20
2 | 2 | Stent | Stent installed/artery expanded | 25 | Katie | 10 | 2 |  | Stent |  |  |  | 95% | 25
3 | 13 | Special Bone Repair | Bone bridge inserted | 15 | Arshia | 10 | 7 |  | 4sb |  |  |  | 75% | 15
4 | 13.1 |  | Only the foot can move/propel the ball | 25 | Arshia | [7 empty] | Open
5 | 1 | Rapid Blood Screening | Syringe in base | 25 | Arshia | 10 | 3 |  | Syringe | Get person |  | 2010-10-30 | in process | 25
6 | 3 | Cardiac Patch | Patch applied | 20 | Arshia | 10 | 5 |  |  |  | w/ Mission 5.0 | 2010-10-30 | Open | 20
6 | 4 | Pace Maker | Pace maker tube end in heart, body is out | 25 | Katie | 10 | 6 |  | kpace |  | w/ Mission 5.0 | 2010-10-30 | in process | 25
7 | 1.2 |  | Number of red blood cells on the field (0-8) | x 5 = | [8 empty] | Open | 40
7 | 7 | Medicine Auto-Dispensing | Blue and whites off, pink is on | 25 | Erikka | 10 | 9 |  | MAD |  | w/ Mission 8.0 |  | in process | 25
7 | 8 | Robotic Sensitivity | Weight all the way up | 25 | Erikka | 10 | 8 |  |  |  | w/ Mission 7.0 | 2010-10-30 | Open | 25
7 | 9 | Object Controlled Through Thought | Door open at least half way | 20 | Erikka | 10 | 11 |  | open door |  |  |  | 25% | 20
7 | 10 | Nerve Mapping | Nerve input/output revealed | 15 | Erikka | 10 | 10 | [5 empty] | Open | 15
7 | 11 | Professional Teamwork | People all together in the patient area | 25 | Erikka | 10 | 14 | [5 empty] | Open
7 | 14 | Common Bone Repair | Set (align) Bone and Set Blue Cast | 25 | Erikka | 10 | 4 |  | CB repair |  |  |  | 100% | 25
| 1.1 |  | All three white blood cells in patient's area | 15 | [5 empty] | w/ 7.1 |  |  | Open
| 7.1 |  | Blue and whites in container in patient area | 5 | [5 empty] | w/ 1.1 |  |  | Open
| 12 | Bad Cell Destruction | Bad cell identification (some black up, rest face north) | 20 | Athena | 10 | 12 |  |  |  |  | 2010-10-30 | Open
| 12.1 |  | *or Bad cell destruction (all black tiles face north) | 25 | [8 empty] | Open
|  |  |  | Total Score | Time Used | 140 | [7 empty] | 305
|  | Notes |  |  | Total Time | 150